## Sheet1
Gannt Chart of the Project
Task | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16
Project Proposal
Determining the dataset | bar: Week 3 to Week 4
Determining the methods | bar: Week 4 to Week 5
Writing the project proposal | bar: Week 6
First Report
Dataset pre-processing | bar: Week 7 to Week 8
Linear Regression Algorithm | bar: Week 9
Literature review for Decision Tree | bar: Week 9 to Week 10
Decision Tree Algorithm | bar: Week 10 to Week 12
Performance Analysis | bar: Week 11 to Week 12
Writing the first report | bar: Week 10 to Week 12
Final Report
Revision based on feedback | bar: Week 13
Literature review for Neural Network | bar: Week 13
Dataset pre-processing for Neural Network | bar: Week 14
Neural Network Algorithm | bar: Week 14 to Week 16
Performance Analysis | bar: Week 16
Writing the final report | bar: Week 14 to Week 16
Defne
Boran
Together